## Action plan
PROJECT STATEMENT Explainig the Why | Value Leadership is a way we do business, the way we behave in our everyday work life. To reinvest in future Growth and Talents we need to find effectiveness in our current work. If not our associates themselves who knows how to make that happen? Value Leadership is global long-term strategy that will help us grow year-on-year. We deploy Value Leadership in line with global OGSM to bring more smiles and have freedom to operate. VL lets us offset cost push and mitigate internal costs in order not to put them onto consumer. To keep pipeline sufficient we want to engage all our associates to share their valuable ideas. This is why we need to build strong awareness of the programme
Objective of this VL communication plan | The communication plan should result into : - Create one VL programme (Supply & Demand) - Together for growth - Create connectivity to GROWTH ; creating opportunities for the whole business- Freedom to operate our business - Deliver / Create long term sustainable program ands pipline of projects, delivering 5 % YoY improvements - Recognise associates, teams and functions who deliver a substantial saving to the business ( It is not only about delivering savings, also gebersating ideas, role model Value leadership, deliver great support to MIH) - Engagement on VL programme; VL = every day behavior; generating Ideas: Every day is valuable. Having great and sufficinet ideas in the pipeline will let us feel safe about future opportunities Each of our associates can create efficiencies by focusing on activities that fuel our flywheel, driving sustainability and reducing non-essential spend It is spending money as if it is your own and working more efficiently to drive savings. It’s eliminating waste and non-value activities, and doing things better
|  |  | As a result of the communication experience | [5 empty] | Context: Business Strategy or initiative |  |  | Tools and Resources
Stakeholder Group | Stakeholder prioritisation | Current level of the emotional impact | They should understand & KNOW | What should they know? (If they are stakholders what they need….) | The emotional impact is that they should FEEL | The call to action is that they should DO | One-off or a programme? What should be achieved BY WHEN | through…. | Tools | Key messages for your team | Other issues to take into account | Media and Communication (exists) | Media and Communication (needed) | Timing/Sequencing | Materials and Resources | Measurement and Tracking
DEMAND
Руководитель региона | Keep satisfied | Keep informed | Количество внедрений в районах региона, процент повышения доходов от аренды и собираемости платежей |  | Keep satisfied |  |  | Informing | ежемесячный доклад о статусе проекта |  |  | ежемесячное совещание | -
Министр имущества региона | Manage closely | Manage closely | Количество внедрений в районах региона, удовлетворенность руководителей муниципалитетов |  | Ownership |  |  | involvming | Проведение стратегических сессий с командой разработки и внедрения, еженедельный доклад один-на-один |  |  | еженедельная планерка с другими предприятиями | приголашение на стратегические сессии с командой, еженедельный доклад в формате 1х1
Министр цифровизации региона | Manage closely | Keep informed | Количество внедрений в районах региона, удовлетворенность руководителей отдело аренды в регионах, повышение выручки от аренды имущества |  | Ownership |  |  | involvming | Проведение стратегических сессий с командой разработки и внедрения, еженедельный доклад один-на-один, сводка отзывов муниципалитетов о работе продукта |  |  | ежемесячный письменный отчет о статусе проекта | приголашение на стратегические сессии с командой, еженедельный доклад в формате 1х1, составление и направление сводки с позитивными отзывами районов
Руководитель муниципалитета | Keep satisfied | Keep satisfied | Увеличение доли дохода от аренды в общих доходах муниципалитета |  | Commitment / Ownership |  |  | Engaging | Ежемесячная встреча с демонстрацией показателей внедрения и изменения доходов муниципалитета, письменное информировани завершении этапа внедрения и запрос разрешения на начало следующего |  |  | ежемесячный письменный отчет о статусе проекта в районе, письменное информировани завершении этапа внедрения и запрос разрешения на начало следующего | Ежемесячная встреча с участием руководителя отдела имущества и аренды муниципалитета
Руководитель отдела аренды имущества и земли в муниципалитете | Keep informed | Keep informed | Снижение времени на обработку договора и обработку единицы имущества/земли в муниципальной собственности, увеличение дохода от аренды в месяц/квартал |  | Commitment / Ownership |  |  | Engaging | Участие в рабочих группах по обсуждению интерфейсов, участие в опросниках, привлечение к обучению |  |  | еженедельный ВКС по проблемным вопросам внедрения и использования продукта | Привлечение к ВКС с рабочей группой с планированием развития продукта, привлечение к составлению методик внедрения и обучения новых сотрудников